## Product Backlog
CallAudit Pro — AI Customer Support Quality Auditor
PRODUCT BACKLOG
US ID | User Story Description | MoSCoW | Category | Business Value | Priority | Risk | Type | Planned Sprint | Actual Sprint | Status | Assignee | Dependency | Recommendation
MUST HAVE
US-001 | As a supervisor, I want to upload call recordings (MP3/WAV/M4A) so that the system can automatically transcribe them using Deepgram Nova-2. | MUST HAVE | Transcription | 100 | 1 | Low | Feature | Sprint 1 | Sprint 1 | 3- Completed | Srivani Tadaka & Grace Maria Reji | No Dependency | Core pipeline entry point
US-002 | As an agent, I want AI to score my call on overall quality (0–100 with Grade A–F) so that I know my performance level. | MUST HAVE | AI Scoring | 100 | 1 | Low | Feature | Sprint 1 | Sprint 1 | 3- Completed | Srivani Tadaka & Grace Maria Reji | US-001 | Uses LangChain + Groq llama-3.3-70b
US-003 | As a supervisor, I want to see violations detected in each call with severity levels (critical/high/medium/low) so that compliance issues are tracked. | MUST HAVE | Compliance | 95 | 1 | Medium | Feature | Sprint 2 | Sprint 2 | 3- Completed | Srivani Tadaka, Grace Maria Reji | US-002 | Alert engine integration required
US-004 | As a supervisor, I want dimension scores (Empathy, Professionalism, Compliance, Resolution, Clarity) so that I can evaluate agent skills precisely. | MUST HAVE | Analytics | 90 | 1 | Low | Feature | Sprint 2 | Sprint 2 | 3- Completed | Srivani Tadaka | US-002 | 5 dimensions, scored 0–10 each
US-005 | As a developer, I want RAG pipeline using ChromaDB/Pinecone to enrich transcripts with similar past calls and policy rules so that scoring is context-aware. | MUST HAVE | RAG / AI | 95 | 1 | High | Technical | Sprint 2 | Sprint 2 | 3- Completed | Srivani Tadaka, Grace Maria Reji | US-001 | Vector similarity search
SHOULD HAVE
US-006 | As a supervisor, I want a real-time live monitoring dashboard so that I can watch calls being scored as they happen. | SHOULD HAVE | Live Monitor | 85 | 2 | High | Feature | Sprint 3 | Sprint 3 | 3- Completed | Srivani Tadaka, Grace Maria Reji | US-001, US-002 | Microphone + Deepgram REST streaming
US-007 | As an agent, I want AI-generated improvement suggestions with example phrases so that I can improve my call handling skills. | SHOULD HAVE | Coaching | 80 | 2 | Low | Feature | Sprint 2 | Sprint 2 | 3- Completed | Srivani Tadaka, Grace Maria Reji | US-002 | Min 2 suggestions per call
US-008 | As a supervisor, I want compliance email alerts triggered automatically when violations exceed thresholds so that issues are escalated immediately. | SHOULD HAVE | Alerts | 80 | 2 | Medium | Feature | Sprint 3 | Sprint 3 | 3- Completed | Srivani Tadaka | US-003 | SMTP-based AlertEngine
US-009 | As a supervisor, I want customer satisfaction metrics (rating 0–5, frustration level, sentiment) so that I can track customer experience. | SHOULD HAVE | Analytics | 80 | 2 | Low | Feature | Sprint 2 | Sprint 2 | 3- Completed | Srivani Tadaka & Grace Maria Reji | US-002 | Extracted from LLM scoring
US-010 | As a supervisor, I want a team Supervisor Dashboard with KPIs, charts, and leaderboards so that I can track team performance across all calls. | SHOULD HAVE | Dashboard | 85 | 2 | Low | Feature | Sprint 4 | Sprint 4 | 3- Completed | Srivani Tadaka & Grace Maria Reji | US-002 | Plotly charts, grade breakdown, trend
COULD HAVE
US-011 | As a supervisor, I want to export all scored calls to an Excel report with 5 sheets so that I can share results offline. | COULD HAVE | Reports | 65 | 3 | Low | Feature | Sprint 4 | Sprint 4 | 3- Completed | Srivani Tadaka | US-002 | openpyxl multi-sheet export
US-012 | As a supervisor, I want to generate a PDF report per call so that I can archive and share individual call audits. | COULD HAVE | Reports | 60 | 3 | Low | Feature | Sprint 4 | Sprint 4 | 3- Completed | Srivani Tadaka | US-002 | ReportLab-based PDF generation
US-013 | As an agent, I want to paste transcripts manually in the Live Analysis page so that I can score calls even without microphone access. | COULD HAVE | UX | 60 | 3 | Low | Feature | Sprint 3 | Sprint 3 | 3- Completed | Srivani Tadaka & Grace Maria Reji | US-002 | Fallback for cloud deployment
US-014 | As a developer, I want model classification metrics (Precision, Recall, F1, Confidence) displayed per call so that scoring quality is measurable. | COULD HAVE | Analytics | 55 | 3 | Low | Feature | Sprint 4 | Sprint 4 | 3- Completed | Srivani Tadaka | US-002 | Returned by LLM in JSON response
WON'T HAVE
US-015 | As a supervisor, I want multi-language transcription support so that non-English calls can also be audited. | WON'T HAVE | Transcription | 40 | 4 | High | Future | Future | — | 1- Not Started | — | No Dependency | Requires multilingual model fine-tuning
US-016 | As an agent, I want a mobile app version of the auditor so that I can review my scores on my phone. | WON'T HAVE | UX | 30 | 4 | Medium | Future | Future | — | 1- Not Started | — | No Dependency | Out of current project scope

## Sprint Backlog
SPRINT 1 ¦ 01/01/2025 → 14/01/2025 ¦ Goal: Set up project foundation: Deepgram transcription pipeline, basic RAG setup with ChromaDB, initial Streamlit UI skeleton.
Task ID | US ID | Task Description | Team Member | Activity | Status | Task Start Date | Task Completion Date | Original Estimate (Hours) | Remaining Effort (Hours)
T-001 | US-001 | Set up project repository and virtual environment | Srivani Tadaka, Grace Maria Reji | Environment Setup | 3- Completed | 2026-02-02 | 2026-02-03 | 4 | 0
T-002 | US-001 | Implement Deepgram REST API transcription (deepgram_processor.py) | Srivani Tadaka, Grace Maria Reji | API Integration | 3- Completed | 2026-02-05 | 2026-02-07 | 8 | 0
T-003 | US-001 | Add audio format support: MP3, WAV, M4A, FLAC with retry logic | Srivani Tadaka, Grace Maria Reji | Feature Development | 3- Completed | 2026-02-05 | 2026-02-07 | 4 | 0
T-004 | US-005 | Researching on ChromaDB vector store and RAG pipeline structure | Srivani Tadaka, Grace Maria Reji | Architecture Design | 3- Completed | 2026-02-09 | 2026-02-15 | 12 | 0
T-005 | US-005 | Implement transcript enrichment with similar past calls injection | Srivani Tadaka, Grace Maria Reji | Data Enrichment | 3- Completed | 2026-02-10 | 2026-02-12 | 8 | 0
T-006 | US-002 | Scaffold Streamlit multi-page app with sidebar navigation | Grace Maria Reji | UI Development | 3- Completed | 2026-02-10 | 2026-02-12 | 6 | 0
T-007 | US-001 | Write unit tests for transcription module | Srivani Tadaka, Grace Maria Reji | Unit Testing | 3- Completed | 2025-01-12 | 2025-01-15 | 4 | 0
NOTES: Task sizing should be between 0.5 to 12 hours
SPRINT 2 ¦ 15/01/2025 → 28/01/2025 ¦ Goal: Implement full AI scoring with LangChain + Groq, dimension scores, violations, satisfaction metrics, and customer sentiment analysis.
Task ID | US ID | Task Description | Team Member | Activity | Status | Task Start Date | Task Completion Date | Original Estimate (Hours) | Remaining Effort (Hours)
T-008 | US-002 | Build LangChain scoring prompt template (SCORING_PROMPT) | Srivani Tadaka | Prompt Engineering | 3- Completed | 2026-02-16 | 2026-02-18 | 10 | 0
T-009 | US-002 | Integrate ChatGroq llama-3.3-70b via langchain_groq | Srivani Tadaka | Model Integration | 3- Completed | 2026-02-17 | 2026-02-20 | 6 | 0
T-010 | US-002 | Implement JSON response parsing with fallback error handling | Grace Maria Reji | Error Handling | 3- Completed | 2026-02-17 | 2026-02-20 | 4 | 0
T-011 | US-004 | Add dimension scoring: Empathy, Professionalism, Compliance, Resolution, Clarity | Srivani Tadaka | Feature Engineering | 3- Completed | 2026-02-19 | 2026-02-21 | 6 | 0
T-012 | US-003 | Implement violations detection with severity levels and quote extraction | Srivani Tadaka, Grace Maria Reji | Rule Engine Development | 3- Completed | 2026-02-19 | 2026-02-21 | 6 | 0
T-013 | US-009 | Add customer satisfaction metrics (frustration, sentiment, rating 0–5) | Srivani Tadaka, Grace Maria Reji | Metrics Implementation | 3- Completed | 2026-02-19 | 2026-02-21 | 4 | 0
T-014 | US-007 | Implement improvement suggestions with example phrases in prompt | Grace Maria Reji | Prompt optimization | 3- Completed | 2026-02-19 | 2026-02-21 | 4 | 0
T-015 | US-005 | Inject KB policy rules into RAG enrichment pipeline | Srivani Tadaka | RAG Enrichment | 3- Completed | 2026-02-23 | 2026-02-26 | 6 | 0
T-016 | US-002 | Fix httpx proxies compatibility issue with Groq + httpx>=0.28 | Srivani Tadaka, Grace Maria Reji | Bug Fixing | 3- Completed | 2026-02-23 | 2026-02-26 | 4 | 0
T-017 | US-002 | Integration test: full pipeline audio→transcript→score | Srivani Tadaka, Grace Maria Reji | Integration Testing | 3- Completed | 2026-02-23 | 2026-02-26 | 4 | 0
NOTES: Task sizing should be between 0.5 to 12 hours
SPRINT 3 ¦ 29/01/2025 → 11/02/2025 ¦ Goal: Build real-time live monitoring with microphone capture, audio chunking, stream transcription, and compliance alert engine.
Task ID | US ID | Task Description | Team Member | Activity | Status | Task Start Date | Task Completion Date | Original Estimate (Hours) | Remaining Effort (Hours)
T-018 | US-006 | Implement AudioCapture with PyAudio (5s WAV chunks, queue-based) | Srivani Tadaka, Grace Maria Reji | Audio Processing | 3- Completed | 2026-02-24 | 2026-02-26 | 10 | 0
T-019 | US-006 | Build StreamTranscriber using Deepgram REST API (Deepgram SDK v6 compatible) | Srivani Tadaka, Grace Maria Reji | Streaming Integration | 3- Completed | 2026-02-24 | 2026-02-27 | 8 | 0
T-020 | US-006 | Implement LiveMonitor orchestrator with threading and periodic scoring | Srivani Tadaka, Grace Maria Reji | Real-time Ochrestration | 3- Completed | 2026-02-25 | 2026-02-27 | 10 | 0
T-021 | US-008 | Build AlertEngine with email notifications (SMTP) for compliance violations | Srivani Tadaka, Grace Maria Reji | Alert System development | 3- Completed | 2026-02-26 | 2026-02-28 | 8 | 0
T-022 | US-013 | Add manual transcript paste fallback in Live Analysis UI | Srivani Tadaka, Grace Maria Reji | UI Enhancement | 3- Completed | 2026-02-27 | 2026-02-28 | 4 | 0
T-023 | US-006 | Fix LiveMonitor.stop() crashing Streamlit (SystemExit from PyAudio) | Srivani Tadaka, Grace Maria Reji | Bug Fixing | 3- Completed | 2026-02-28 | 2026-02-28 | 6 | 0
T-024 | US-006 | Add live badge, real-time transcript viewer in Streamlit UI | Srivani Tadaka, Grace Maria Reji | Ui Development | 3- Completed | 2026-03-01 | 2026-03-03 | 4 | 0
T-025 | US-006 | Integration and regression test: live monitor full flow | Srivani Tadaka, Grace Maria Reji | Integration Testing | 3- Completed | 2026-03-02 | 2026-03-04 | 4 | 0
NOTES: Task sizing should be between 0.5 to 12 hours
SPRINT 4 ¦ 12/02/2025 → 25/02/2025 ¦ Goal: Build Supervisor Dashboard with analytics, leaderboards, charts, and full Reports page with PDF and Excel export.
Task ID | US ID | Task Description | Team Member | Activity | Status | Task Start Date | Task Completion Date | Original Estimate (Hours) | Remaining Effort (Hours)
T-026 | US-010 | Implement load_results() and result persistence as JSON files | Srivani Tadaka, Grace Maria Reji | Data Persistance | 3- Completed | 2026-03-02 | 2026-03-04 | 4 | 0
T-027 | US-010 | Build Supervisor Dashboard KPI metrics row (6 KPIs) | Srivani Tadaka, Grace Maria Reji | Dashboard Development | 3- Completed | 2026-03-03 | 2026-03-05 | 6 | 0
T-028 | US-010 | Add Plotly charts: score distribution, grade breakdown, dimension averages, trend | Srivani Tadaka, Grace Maria Reji | Data Visualization | 3- Completed | 2026-03-04 | 2026-03-06 | 10 | 0
T-029 | US-010 | Implement violations severity pie chart and outcome breakdown pie chart | Srivani Tadaka, Grace Maria Reji | Data Visualization | 3- Completed | 2026-03-04 | 2026-03-06 | 4 | 0
T-030 | US-010 | Build leaderboard: Best 5 and Worst 5 calls with grade cards | Srivani Tadaka, Grace Maria Reji | Feature Development | 3- Completed | 2026-03-05 | 2026-03-08 | 4 | 0
T-031 | US-010 | Add filter panel: grade, outcome, score range with dynamic DataFrame | Srivani Tadaka, Grace Maria Reji | UI Enhancement | 3- Completed | 2026-03-05 | 2026-03-09 | 4 | 0
T-032 | US-011 | Implement Excel report generator (5 sheets: Summary, Calls, Violations, Improvements, Agent Quality) | Srivani Tadaka, Grace Maria Reji | Report Generation | 3- Completed | 2026-03-08 | 2026-03-09 | 8 | 0
T-033 | US-012 | Implement PDF report generator using ReportLab | Srivani Tadaka, Grace Maria Reji | Report Generation | 3- Completed | 2026-03-08 | 2026-03-09 | 6 | 0
T-034 | US-014 | Add model metrics display (Precision, Recall, F1, Confidence) | Srivani Tadaka, Grace Maria Reji | Model Evaluation | 3- Completed | 2026-03-08 | 2026-03-12 | 2 | 0
T-035 | US-011 | System test: reports download and verify content | Srivani Tadaka, Grace Maria Reji | System Testing | 3- Completed | 2026-03-09 | 2026-03-12 | 4 | 0
NOTES: Task sizing should be between 0.5 to 12 hours
SPRINT 5 ¦ 26/02/2025 → 11/03/2025 ¦ Goal: UI polish, bug fixes, Pinecone cloud vector backend support, Streamlit Cloud deployment, and final system testing.
Task ID | US ID | Task Description | Team Member | Activity | Status | Task Start Date | Task Completion Date | Original Estimate (Hours) | Remaining Effort (Hours)
T-036 | US-005 | Add Pinecone vector backend support as alternative to ChromaDB | Srivani Tadaka, Grace Maria Reji | Backend Integration | 3- Completed | 2026-03-12 | 2026-03-14 | 8 | 0
T-037 | US-002 | Apply dark theme CSS: custom colours, metric cards, violation cards | Srivani Tadaka, Grace Maria Reji | UI styling | 3- Completed | 2026-03-14 | 2026-03-15 | 6 | 0
T-038 | US-002 | Add summary card (Grade badge + Score + AI Summary) at top of results | Srivani Tadaka, Grace Maria Reji | UI Enhancement | 3- Completed | 2026-03-14 | 2026-03-15 | 4 | 0
T-039 | US-001 | Fix audio transcription showing result immediately after upload | Srivani Tadaka, Grace Maria Reji | Bug fixing | 3- Completed | 2026-03-15 | 2026-03-17 | 4 | 0
T-040 | US-006 | Fix Deepgram SDK v6 breaking change in StreamTranscriber | Srivani Tadaka, Grace Maria Reji | Bug fixing | 3- Completed | 2026-03-16 | 2026-03-18 | 6 | 0
T-041 | US-006 | Harden AudioCapture: queue-based chunk writer, safe stop(), SystemExit guard | Srivani Tadaka, Grace Maria Reji | Performance Optimization | 3- Completed | 2026-03-18 | 2026-03-19 | 6 | 0
T-042 | US-001 | Configure Streamlit Cloud secrets and deployment (app_cloud.py) | Srivani Tadaka, Grace Maria Reji | Deployment | 3- Completed | 2026-03-18 | 2026-03-20 | 4 | 0
T-043 | US-002 | Full regression test: Dashboard → Live → Supervisor → Reports flow | Srivani Tadaka, Grace Maria Reji | Regression Testing | 3- Completed | 2026-03-19 | 2026-03-26 | 6 | 0
T-044 | US-002 | Final documentation and code review | Srivani Tadaka, Grace Maria Reji | Documentation & Code review | 3- Completed | 2026-03-19 | 2026-03-26 | 4 | 0
NOTES: Task sizing should be between 0.5 to 12 hours

## Stand up Meeting
CallAudit Pro — Daily Standup Meeting Log | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7
Sprint # | Date | Team Member | Activity | Status | Impediments | Action Taken | SL #
1 | 2026-02-05 | Srivani Tadaka, Grace Maria Reji | Project setup, API integration, RAG setup | 3- Completed | Initial clarity on vector DB | Reviewed docs & mentor support | 1
2 | 2026-02-17 | Srivani Tadaka, Grace Maria Reji | LLM integration, prompt design, JSON parsing | 3- Completed | httpx proxy issue | Patched httpx client | 2
2 | 2026-02-20 | Srivani Tadaka, Grace Maria Reji | Scoring, violations, satisfaction metrics | 3- Completed | None | _ | 3
3 | 2026-02-25 | Srivani Tadaka, Grace Maria Reji | Audio capture, transcription, streaming pipeline | 3- Completed | SDK breaking changes | Switched to REST API | 4
3 | 2026-03-04 | Srivani Tadaka, Grace Maria Reji | Live monitoring, alert engine, UI fallback | 3- Completed | Streamlit crashes | Handled exceptions safely | 5
4 | 2026-02-16 | Srivani Tadaka, Grace Maria Reji | Dashboard, reports (Excel/PDF), analytics | 3- Completed | None | — | 6
5 | 2026-02-23 | Srivani Tadaka, Grace Maria Reji | Deployment, testing, bug fixes | 3- Completed | None | — | 7
| 2026-02-25 | Srivani Tadaka, Grace Maria Reji | Documentation & Code Review | 3- Completed | None | —

## Retrospection
CallAudit Pro — Sprint Retrospection
Sprint # | Start Doing | Stop Doing | Continue Doing | Team Member Name
1 | Writing unit tests alongside feature development to catch integration issues early. | Assuming project requirements are clear without verifying with the mentor first. | Conducting daily standups to surface blockers quickly; using ChromaDB for local vector testing. | Srivani Tadaka, Grace Maria Reji
2 | Monkey-patching library compatibility issues (httpx proxies) at module load time before imports. | Rushing through complex LangChain prompt design without validating JSON output structure first. | Iterative prompt testing with sample transcripts before full pipeline integration. | Srivani Tadaka, Grace Maria Reji
3 | Using queue-based threading patterns for audio capture to decouple recording from transcription. | Relying on Deepgram SDK version assumptions — always use REST API directly for version safety. | Wrapping all Streamlit button callbacks in full try/except to prevent server crashes. | Srivani Tadaka, Grace Maria Reji
4 | Building reusable render_result_dashboard() component shared across all pages. | Delaying review of Plotly chart colour schemes — should align with dark theme earlier. | Reviewing documentation regularly; using Plotly for all charts for consistent styling. | Srivani Tadaka, Grace Maria Reji
5 | Performing full regression testing after each bug fix before committing. | Delaying final deployment configuration until the last sprint — should be done earlier. | Collaborating on debugging sessions; maintaining focus on core features before polish. | Srivani Tadaka, Grace Maria Reji